# AirWise Founder Execution Sheet

Last updated: 2026-04-14

## Objective

Translate the 90-day roadmap into a founder operating sheet that assigns weekly ownership across:

- product

- engineering

- pilot operations

- sales / GTM

This assumes two founders:

- `Technical Founder / CEO`: product strategy, engineering, infrastructure, UX, delivery, data model, AI/document workflows

- `Domain / GTM Cofounder`: customer access, pilot execution, building operations context, workflow validation, sales pipeline

Optional support:

- `BACnet / controls contractor`

- `RDP / RCxA advisor`

- `design partner building staff`

## Operating rules

- Every week must end with one demoable artifact.

- Product decisions should be validated against at least one real building.

- Sales activity should always be tied to pilot readiness, not detached outreach.

- Engineering should not block on perfect BAS integration if compliance workflows can keep moving.

- Any write-back capability requires explicit customer-side governance before activation.

## Weekly execution sheet

| Week | Product Owner | Engineering Owner | Pilot Ops Owner | Sales / GTM Owner | Weekly Deliverable |

|---|---|---|---|---|---|

| 1 | Define MVP workflow and screens for portfolio, building, compliance, documents | Set up repo, environments, auth, DB, queue, storage | Create pilot intake checklist and customer data request list | Confirm pilot target account, stakeholders, and decision-maker map | MVP scope doc + pilot intake pack |

| 2 | Finalize information architecture and data model priorities | Create initial schema and config tables for pathways, penalties, PECMs, limits | Gather sample building roster and sample docs | Lock pilot discovery meetings and request BAS/sensor access info | Schema v1 + sample intake data |

| 3 | Define building overview and portfolio import UX | Build portfolio import and building resolver | Validate imported buildings against owner truth | Advance pilot discussion toward committed test buildings | Imported pilot roster with conflicts list |

| 4 | Define confidence/conflict UX and manual review flow | Implement identity resolution, review states, building overview page | Resolve address/BBL/BIN mismatches with customer | Confirm which buildings are in compliance pilot vs monitoring pilot | Canonical building graph for pilot set |

| 5 | Define compliance workspace layout for Article 320 and 321 | Build pathway resolver and requirement generator | Review outputs against DOB docs and owner records | Position AirWise around compliance workflow value in pilot conversations | Compliance workspace skeleton |

| 6 | Define portfolio compliance dashboard and blocker visibility | Implement Article 320 + 321 workspaces and dashboard | Validate pathway results, PECM applicability, and terminology | Convert design-partner interest into pilot scope and commercial terms | Real building readiness dashboard |

| 7 | Define document/evidence UX and audit trail | Build upload, classification state, evidence links, audit entries | Collect and upload representative real documents | Use demo to support pilot close and stakeholder confidence | Evidence workflow v1 |

| 8 | Refine requirement/evidence states based on real documents | Implement readiness recalculation and document review states | Review missing evidence and assign follow-ups | Finalize pilot SOW / success criteria / access plan | Compliance + evidence demo using real docs |

| 9 | Define monitoring overview, issue cards, and operator task UX | Build telemetry ingest, time-series store, BACnet discovery pipeline | Coordinate BAS or gateway access and point list availability | Keep pilot stakeholders aligned on monitoring scope and building access | First telemetry and discovery ingest |

| 10 | Define point mapping review workflow and system detail page | Store devices/points, implement mapping admin flow, polling | Validate mapped systems with operator/contractor | Prepare pilot narrative for monitoring value, not just compliance | Mapped pilot ventilation system |

| 11 | Define issue detection outputs and recommendation UX | Implement issue rules and recommendation generation | Review issues with operator/engineer and tune thresholds | Use live issues as proof of operational insight in customer conversations | Recommendations v1 |

| 12 | Define before/after workflow and intervention logging UX | Implement intervention tracking and before/after reporting | Get operator follow-through on recommended actions | Convert recommendation evidence into expansion narrative | First completed recommendation outcome |

| 13 | Define command request/approval UX and safety notices | Implement whitelist model, command request flow, approval roles | Confirm customer-side approval chain and restricted systems | Align customer expectations on supervised control vs automation | Command workflow v1 |

| 14 | Define rollback and command audit UX | Implement execution, expiry, rollback, and logs | Validate approved write categories with BAS specialist | Use controlled write-back as trust-building pilot milestone | Successful supervised test command |

| 15 | Prioritize pilot polish, KPI summaries, and reporting outputs | Fix critical bugs, improve dashboards, add KPI summaries | Collect pilot feedback and unresolved blockers | Prepare pilot review deck and expansion path | Pilot review build |

| 16 | Define next-phase roadmap from actual usage | Close critical bugs, stabilize exports, package learnings | Run pilot retrospective with customer and partners | Push for annual contract / expansion / next portfolio | Customer-ready pilot outcome package |

## Function-by-function founder ownership

## Product

### Technical Founder / CEO

Owns:

- product scope and sequencing

- UX for portfolio, compliance, monitoring, and command workflows

- prioritization decisions

- requirements tradeoffs

- weekly demo narrative

Must deliver each week:

- updated MVP decision log

- current workflow spec

- clear acceptance criteria for the next build slice

### Domain / GTM Cofounder

Owns:

- validating that product workflows reflect real owner/operator behavior

- reviewing terminology, tasks, and evidence requirements

- confirming that outputs are useful in actual customer meetings

Must deliver each week:

- product feedback grounded in at least one real building or stakeholder

- list of confusing, missing, or non-credible workflow elements

## Engineering

### Technical Founder / CEO

Owns:

- architecture

- schema and APIs

- frontend implementation

- backend implementation

- telemetry and command safety logic

- infra and deployment

- observability

Must deliver each week:

- one demoable product increment

- updated docs/specs where logic changed

- visible blocker list

### BACnet / controls contractor

Owns when engaged:

- BAS access assumptions

- point classification guidance

- safe write categories

- rollback realism

Must deliver when engaged:

- reviewed point maps

- approved or rejected write candidates

- list of control risks

## Pilot Operations

### Domain / GTM Cofounder

Owns:

- building intake coordination

- document collection

- stakeholder routing

- BAS access coordination

- operator task follow-up

- pilot meeting cadence

Must deliver each week:

- current pilot status sheet

- list of blockers by building

- next actions assigned to customer or internal team

### Technical Founder / CEO

Owns support for pilot ops through:

- import tools

- evidence workflows

- dashboards

- logs and troubleshooting

Must deliver each week:

- tools that reduce manual pilot coordination

- instrumentation to see what is failing

## Sales / GTM

### Domain / GTM Cofounder

Owns:

- pilot close

- expansion path inside first account

- warm intro pipeline

- stakeholder mapping

- meeting follow-up

- commercial framing

Must deliver each week:

- account status update

- open commercial questions

- next-step asks for each stakeholder

### Technical Founder / CEO

Owns support for GTM through:

- live product demos

- technical credibility in customer meetings

- roadmap framing

- scoped answers to integration and deployment questions

Must deliver each week:

- updated demo environment

- technically credible answers to customer objections

## Weekly founder meeting template

### 1. Product review

- What shipped last week?

- What is demoable now?

- What changed in the acceptance criteria?

### 2. Pilot review

- Which buildings advanced?

- What data is missing?

- What access is blocked?

- What operator actions are pending?

### 3. Sales review

- Is the pilot moving toward commitment or expansion?

- What objections came up?

- What proof is still missing for the buyer?

### 4. Risk review

- compliance interpretation risks

- data quality risks

- BAS access risks

- customer adoption risks

- command safety risks

### 5. Next-week lock

- one product deliverable

- one pilot milestone

- one sales milestone

## Scorecard to review every Friday

### Product

- Was a demoable increment shipped?

- Is the critical path still on track?

- Were any safety or compliance assumptions changed?

### Engineering

- Are APIs/schema stable enough for the next week?

- Are there new technical blockers?

- Is observability sufficient to debug pilot issues?

### Pilot Ops

- Did at least one building advance materially?

- Did document completeness improve?

- Did telemetry / BAS access improve?

### Sales

- Did stakeholder confidence increase?

- Is pilot scope clearer?

- Is the path to paid expansion stronger?

## Founder-level KPIs

### Technical Founder / CEO

- `% roadmap tasks shipped on time`

- `% pilot blockers caused by product gaps`

- `time to resolve critical pilot bug`

- `number of demoable features shipped`

### Domain / GTM Cofounder

- `pilot stakeholder response time`

- `% requested documents received`

- `% pilot buildings with validated facts`

- `pilot progression from interest to scoped commitment`

### Shared KPIs

- `% buildings resolved to pathway`

- `% buildings with usable readiness views`

- `number of actionable ventilation issues detected`

- `recommendation acceptance rate`

- `pilot-to-expansion probability`

## Escalation rules

- If compliance facts conflict with owner data, escalate immediately and do not silently choose one source.

- If BAS access is delayed more than one week, switch to read-only/replayed data plan rather than blocking the roadmap.

- If command safety is uncertain, disable write-back and continue recommendation-only mode.

- If the pilot account stalls commercially, use the product artifacts to open the second design-partner path in parallel.